## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Nameera Mahek | 2024-12-20 | Error with extraction via API | S2 | Nameera Mahek | Bugs | Adhered to the bank policy and extraction documents | 2024-12-20 | Open | Require further investigation
2 | Nameera Mahek | 2025-01-13 | Error with OCR text extraction accuracy | S3 | Nameera Mahek | bugs | Adopted Pre-processing techniques | 2025-01-13 | Closed | Enhanced the accuarcy
3 | Nameera Mahek | 2025-01-20 | Error with llm model fine-tuning | S6 | Nameera Mahek | complexity | Utilized distilled versions for better performace | 2025-01-20 | Closed | Improved performance

## Sheet2
Logical
User Interface
Maintainability
Standards
Others